## Agenda Sharing
SHARING AGENDA
No | STEPS | DURATION (mins)
1 | Overview of Project | 1
2 | Key activities | 1
3 | Project implementation progress | 5
4 | Project Achievement/Results (up to now) | 1
5 | Get support if needed | 1
6 | Next steps | 1
10

## Factory Project
2026-PROJECT TRACKING | [19 empty] | MONTHLY TRACKING | [11 empty] | Q1 |  |  |  | Q2 |  |  |  | Q3 |  |  |  | Q4 |  |  |  | FY 2026
KEY DRIVER | FACTORY TARGET | TARGET | No | PROJECT NAME | KEY ACTIVITY | LEADER | DEPT | KEY PARTNER SUPPORTER | TEAM MEMBER | COST SAVING (Yes/No) | COST INVESTMENT (Yes/No) | PROJECT CHARTER (Yes/No) | PROJECT CHARTER COMPLETED | TARGET 2026 | TIMING | STATUS | COACH | SPONSER | TRACKING PRIORITY | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec | INITIAL VOLUME SAVING (tons) | ACTUAL VOLUME SAVING (tons) | INITIAL COST SAVING (USD) | ACTUAL COST SAVING (USD) | INITIAL VOLUME SAVING (tons) | ACTUAL VOLUME SAVING (tons) | INITIAL COST SAVING (USD) | ACTUAL COST SAVING (USD) | INITIAL VOLUME SAVING (tons) | ACTUAL VOLUME SAVING (tons) | INITIAL COST SAVING (USD) | ACTUAL COST SAVING (USD) | INITIAL VOLUME SAVING | ACTUAL VOLUME SAVING (tons) | INITIAL COST SAVING | ACTUAL COST SAVING | INITIAL VOLUME SAVING (tons) | ACTUAL VOLUME SAVING (tons) | INITIAL COST SAVING (USD) | ACTUAL COST SAVING (USD)
OUTPUT | Volume (tons FD) | 5550 | 1 | Sustain speed of FD at 750 kg/h | Increase TS = 49% (Done) Standardize FD parameters after increase TS to 49% (Done) | Duy Le | OPs | Trieu Phan | Evap/FD team | Yes | No | Yes | Done | 750kg FD/Hr | Mar | Done | Hai Le | Hai Le |  | NA | NA | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | 17.6 | 18.4 |  |  | 18.9 |  |  |  | 19.2 |  |  |  | 19.2 |  |  |  | 74.9 | 18.4
OUTPUT | Volume (tons FD) | 5550 | 2 | Reduce OPL <2.5% | Revisit & Reduce OPL 2025 Create/update the operations std --> Action pending Average: Jan to May: 3.14% | Vu Le | OPs | Duy Le | All Process | Yes | No | Yes | Done | < 2.5% | Jun Sep | Late | Duy Pham | Hai Le | 1 | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: NA; MONTHLY TRACKING Apr: NA; MONTHLY TRACKING May: NA; MONTHLY TRACKING Jun: 2; MONTHLY TRACKING Jul: 2 | 3.9 | 29.2 |  |  | 4.2 |  |  |  | 4.3 |  |  |  | 4.3 |  |  |  | 16.7
CUSTOMER COMPLAINT | No. of major complaint | 0 | 10 | Q-line mapping for Micro (Reduce 50% NCP due to Micro) | With Production: Normal production: 100% production normal operation mapped CIP/COP: 100% cleaning operation mapped: - Risk assessment & Key action focus: Done. - Proactive alarm & prevent micro growth at stages at previous evap - On going - Key focus: + Micro from Sediment & Prevent Growth Set tank (<15 độ). + Prevent Cross - Contamination: WB, FMT | Binh Dang | QA | Vu Le | Triều Phan, Đức Nguyễn | No | Yes | Yes | Done | Reduce 50% NCP vs 2025 (64 tons) | Jun | Done | Dung Tran | Thi Nguyen |  | NA | NA | 1 | NA | NA | 4 | NA | NA | NA | NA | NA | NA | [17 empty] | 0
OUTPUT | Liquid Extract (tons Liquid) | 494 | 4 | Increase capacity of Devex line to 780 kgs/h --> Actual: 760 kg/hr | Increase cell load from 395 -> 400 Actual: 400 (Done) Reduce cycle time from 19 -> 17 Actual: 18 mins (On going) -Done Increase Evap running time from 32 hrs to 48 hrs Actual: 40 hrs (Done) | Quang Vu | OPs | Trieu Phan | Ext team | Yes | No | Yes | Done | Stable 780kg/hr | Mar Apr May Jul | late | Vu Tran | Duc Mai | 2 | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: 1; MONTHLY TRACKING Apr: 1; MONTHLY TRACKING May: 1; MONTHLY TRACKING Jun: 2; MONTHLY TRACKING Jul: 2 | 66.3 | 60.4 |  |  | 71.4 |  |  |  | 72.2 |  |  |  | 72.2 |  |  |  | 282.1 | 60.4
OUTPUT | Volume (tons FD) | 5550 | 5 | Reduce Monthly Planned Stop at Extraction from 46 hours to 38 hours MTD: 42,5 hrs | Reduce EXT CIP from 16 hours to 14 hours. Actual: 16 (On going) - CIP program 10 cell thay cho CIP 5 cell/1 lần - Done - Trial CIP không tháo Bottom Filter -Done - Các task tháo mở top filter, thiết bị để CIP -> Phối hợp bảo trì để làm nhanh nhất có thể. Reduce Pressure Test & Start up from 12hrs to 8 hours. Actual 11 hrs (On going) - Trial Pressure test bằng Steam, thay bằng nước- đã trial 1 lần vào tháng 2 -Done - Tăng cường nhân lực kiểm tra trong quá trình thay ống và valve để giảm mistake. | Quang Vu | OPs | Nam Tran | Ext team | Yes | No | Yes | Done | PS of EXT: 38 hrs | Mar Apr May Jul | late | Hai Le | Hai Le | 2 | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: 1; MONTHLY TRACKING Apr: 1; MONTHLY TRACKING May: 1; MONTHLY TRACKING Jun: 2; MONTHLY TRACKING Jul: 2 | 12 | 6.3 |  |  | 18 |  |  |  | 18 |  |  |  | 18 |  |  |  | 66 | 6.3
COST | Yield of VG2 Yield of Conilon | 2.01 2.00 | 12 | Sustain yield 60.5% Sustain: 60.5% | Re-visit & reduce OPL 2025 of Extraction Top 3 issues: 1. Bottom filter blockage - Plan thay ống định kỳ hàng tháng - opimize lại plan thay ống hiệu quả. Phối hợp với MT cùng nhau work trong ngày shutdown 2. SE & PE filter are blockage - SE: Gắn thêm đường ống song song - có thể chạy by pass - PE: Gắn thêm 1 Rotary Fillter -> swith chạy qua lại -> Giảm downtime. (Pending ) - PE: Gắn đường ống say Rotary valve lớn hơn, Gắn đường nước rửa cho lọc + đường ống PE sau lọc -Done 3. Piping blockage of the end of cycle - Plan thay ống định kỳ hàng tháng - opimize lại plan thay ống hiệu quả. Phối hợp với MT cùng nhau work trong ngày shutdown | Quang Vu | OPs | Trieu Phan | Ext team | Yes | No | Yes | Done | Sustain 60.5% | Mar Apr May Jul | late | Vu Tran | Duc Mai | 2 | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: 1; MONTHLY TRACKING Apr: 1; MONTHLY TRACKING May: 1; MONTHLY TRACKING Jun: 2; MONTHLY TRACKING Jul: 2 | 3.8 | 1.15 |  |  | 4 |  |  |  | 4.1 |  |  |  | 4.1 |  |  |  | 16 | 1.15
OUTPUT | RW Generation (tons) | 50 | 7 | Reduce RW generation MTD: 1420 kg | Reduce/Eliminate the defect 2025 - Done Finetuning the standard & SOP - Done Final CHO matrix - Done | Vu Le | OPs | Quyet Nguyen | FD/FP team | Yes | No | Yes | Done | < 50 tons | Apr | Done | Duy Pham | Hai Le |  | NA | NA | NA | 4 | NA | NA | NA | NA | NA | NA | NA | NA | 14 | 20.1 |  |  | 14 |  |  |  | 14 |  |  |  | 14 |  |  |  | 56
OUTPUT | Volume (tons FD) | 5550 | 6 | Reduce Monthly Planned Stop at Extraction from 46 hours to 38 hours MTD: 17 hrs | Reduce Maintenance time from 18 hrs to 16hrs | Nam Truong | Eng | Quang Vu |  | Yes | Yes | Yes | Done |  | Apr May Jun Jul Sep | late | Duy Nguyen | Thi Nguyen | 3 | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: NA; MONTHLY TRACKING Apr: 1; MONTHLY TRACKING May: 2; MONTHLY TRACKING Jun: 2; MONTHLY TRACKING Jul: 2
COST | Yield of VG2 Yield of Conilon | 2.01 2.00 | 13 | Sustain yield 60.5% | Re-visit & reduce EPL 2025 of Extraction | Nam Truong | Eng |  |  | Yes | Yes | Yes | Done | Sustain 60.5% | Mar Apr May Jun Jul Sep | late | Duy Nguyen | Thi Nguyen | 3 | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: 1; MONTHLY TRACKING Apr: 1; MONTHLY TRACKING May: 2; MONTHLY TRACKING Jun: 2; MONTHLY TRACKING Jul: 2 | [17 empty] | 0
CUSTOMER COMPLAINT | No. of other complaint | 6 | 11 | Q-line mapping for FB (Reduce 90% wet RW volume due to FB) | With Production: Normal production: 100% production normal operation mapped CIP/COP: 100% cleaning operation mapped: - Priority key Machine to control: Done - Proactive to tracking FB generate from Mainteanance activity (QA verify Shutdown list taks & MoC) - Done Key Focus: + FD movement parts machine (CLeaning & Maintenace) + PM at FP | Binh Dang | QA | Vu Le | Duy Lê | No | Yes | Yes | Done | Reduce 90% RW vs 2025 (37 tons) | Jun | Done | Dung Tran | Thi Nguyen |  | NA | NA | 1 | NA | NA | 4 | NA | NA | NA | NA | NA | NA | [17 empty] | 0
COST | COP (USD/Kg FD) | 2.32 | 28 | Reduce cost 5% spare part for Extraction and Transport system | Savings cost of spare part fabrication workshop Contribute to reduce the store spare part over 36 months costs 10% Refurbishing part to reduce purchasing | Nam Truong | Eng | Anh Truong |  | Yes | No | No | NA |  | Jul Sep | Late |  |  | 3 | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: NA; MONTHLY TRACKING Apr: NA; MONTHLY TRACKING May: NA; MONTHLY TRACKING Jun: NA; MONTHLY TRACKING Jul: 2
OUTPUT | Volume (tons FD) | 5550 | 9 | Reduce Monthly Planned Stop at Extraction from 46 hours to 38 hours | Reduce CIP time by installing a new tank to collect wastewater from Extraction CIP (Utility) Actual: Survey, SOW, PR =>Done, ongoing next steps | Nam Tran | Eng |  |  | Yes | Yes | Yes | Done | PS of EXT: 38 hrs | Mar Apr May Jun Jul | Done | Thang Cao | Thi Nguyen |  | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: 2; MONTHLY TRACKING Apr: 1; MONTHLY TRACKING May: 1; MONTHLY TRACKING Jun: 2; MONTHLY TRACKING Jul: 4 | [17 empty] | 0
COST | Yield of VG2 Yield of Conilon | 2.01 2.00 | 14 | Sustain yield 60.5% | Re-visit & reduce UPs 2025 of Utility | Nam Tran | Eng |  |  | Yes | No | No | NA | Sustain 60.5% | Jun Jul | Late | Thang Cao | Thang Cao | 4 | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: NA; MONTHLY TRACKING Apr: NA; MONTHLY TRACKING May: NA; MONTHLY TRACKING Jun: 2; MONTHLY TRACKING Jul: 2
COST | COP (USD/Kg FD) | 2.32 | 20 | Reduce city water usage | Saving RO reject to RAW water tank | Nam Tran | Eng |  |  | Yes | Yes | Yes | Done |  | Jun | Done | Thang Cao | Thi Nguyen |  | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: NA; MONTHLY TRACKING Apr: NA; MONTHLY TRACKING May: NA; MONTHLY TRACKING Jun: 4
COST | Yield of VG2 Yield of Conilon | 2.01 2.00 | 15 | Sustain moisture at range 2.5% - 2.9% On going | Green Belt DMAIC project | Duy Le | OPs | Vu Tran | FD team | Yes | Yes | Yes | Done | 2.5% - 2.9% Moisture of FD | Sep | On Progress | Outsourcing | Thi Nguyen | [13 empty] | 0 | 0 |  |  | 6.4 |  |  |  | 6.5 |  |  |  | 6.5 |  |  |  | 19.4 | bar: MONTHLY TRACKING Jan to MONTHLY TRACKING Jul
SAFETY | Loss time incident | 0 | 16 | Burn protection | 100% flanges are covered at 2nd floor --> Installed | Nam Truong | Eng |  |  | No | No | No | NA | 100% covered | Mar Apr May Jun | Done | Hoang Nguyen | Thang Cao |  | NA | NA | NA | 4 | NA | NA | NA | NA | NA | NA | NA | NA
COST | Yield of VG2 Yield of Conilon | 2.01 2.00 | 17 | Reduce manufacturing loss from 5% to 4.5% | Finetuning the parameters of Clarifiers & Evaporation. Actual: 4% (Done) - Clarifiers: Empty tank->displace coffee->standby mode ->water mode -> done +Install dual filter 200 micron - Evaporation: + Install and set VFD for Agritator 15hz +CIP 32 - > 40h -> done +CIP 40h -> 48 : On progress (Support Ext capacity) --> Monitor data in Apr | Trieu Phan | OPs | Quyet Nguyen | Evap team | Yes | No | Yes | Done | < 4.5% | Mar | Done | Hai Le | Hai Le |  | NA | NA | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA | 6.6 | 6.9 |  |  | 7.1 |  |  |  | 7.2 |  |  |  | 7.2 |  |  |  | 28.1 | 6.9
SAFETY | Loss time incident | 0 | 26 | Fire protection | Zero error fire alarm issue --> Đã lên PR --> Review -> Lên PO trong tháng 5 - Sep | Nam Tran | Eng |  |  | No | Yes | Yes | Done | Zero error fire alarm issue | Mar Apr May Jun Aug | late | Hoang Nguyen | Thi Nguyen | 4 | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: 1; MONTHLY TRACKING Apr: 1; MONTHLY TRACKING May: 1; MONTHLY TRACKING Jun: 2; MONTHLY TRACKING Jul: 2 | [17 empty] | 0
COST | COP (USD/Kg FD) | 2.32 | 21 | Reduce city water usage | Re-use condensate water and bad Aroma to WWTP - Ongoing - Oct | Nam Tran | Eng |  |  | Yes | Yes | Yes | Done |  | Jun Aug | Late | Thang Cao | Thi Nguyen | 4 | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: NA; MONTHLY TRACKING Apr: NA; MONTHLY TRACKING May: NA; MONTHLY TRACKING Jun: 2; MONTHLY TRACKING Jul: 2
COST | COP (USD/Kg FD) | 2.32 | 27 | Reduce Maintenance Opex in Utility | Optimize spare part of WTP Find local supplier to reduce spare part price (similar quality) | Nam Tran | Eng | Hung Le |  | Yes | No | No | NA |  | Jun Jul | Late |  |  | 4 | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: NA; MONTHLY TRACKING Apr: NA; MONTHLY TRACKING May: NA; MONTHLY TRACKING Jun: 2; MONTHLY TRACKING Jul: 2
COST | COP (USD/Kg FD) | 2.32 | 18 | Reduce city water usage | Re-use condensate water from process | Quyet Nguyen | OPs | Vu Le |  | Yes | Yes | Yes | Done |  | Jun | Done | Vu Tran | Hai Le |  | NA | NA | NA | NA | NA | 4 | NA | NA | NA | NA | NA | NA | 0 | 0 |  |  | 3440 m3 |  |  |  | 3440 m3 |  |  |  | 3440 m3 |  |  |  | 10280 m3
COST | COP (USD/Kg FD) | 2.32 | 38 | Reduce WWT cost | Burn sludge from WWT Plant in Boiler Study to Sale sludge to Fertilizer | Nam Tran | Eng | Hung Le |  | Yes | Yes | Yes | Done |  | Jun Sep | Late | Thang Cao | Thi Nguyen | 4 | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: NA; MONTHLY TRACKING Apr: NA; MONTHLY TRACKING May: NA; MONTHLY TRACKING Jun: 2; MONTHLY TRACKING Jul: 2 | [17 empty] | 0
COST | COP (USD/Kg FD) | 2.32 | 23 | Reduce city water usage | Change makeup water for Boiler from RO to soft water - Done | Nam Tran | Eng |  |  | Yes | Yes | Yes | Done | Changed | Jan | Done | Thang Cao | Thang Cao |  | NA | NA | 4 | NA | NA | NA | NA | NA | NA | NA | NA | NA
SAFETY | Loss time incident | 0 | 31 | CSD (Critical Safety Device) | Apply CSD for dust at boiler --> Aligned with a Hoàng to implementation --> Sent the CSD | Nam Tran | Eng |  |  | No | No | No | NA |  | Mar Apr May Jun | Done | Hoang Nguyen | Thi Nguyen |  | NA | NA | NA | 1 | 2 | 4 | NA | NA | NA | NA | NA | NA
COST | COP (USD/Kg FD) | 2.32 | 25 | Reduce Electric usage | Install solar system (6.6% generate contribution) --> Installed | Duc Nguyen | Eng |  |  | Yes | Yes | Yes | Done |  | Apr | Done | Thang Cao | Thi Nguyen |  | NA | NA | NA | 4 | NA | NA | NA | NA | NA | NA | NA | NA
COST | COP (USD/Kg FD) | 2.32 | 22 | Reduce city water usage | Reuse condensate from process for WWTP - On going Oct | Nam Tran | Eng |  |  | Yes | Yes | Yes | Done |  | Jul | Late | Thang Cao | Thi Nguyen | 4 | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: NA; MONTHLY TRACKING Apr: NA; MONTHLY TRACKING May: NA; MONTHLY TRACKING Jun: NA; MONTHLY TRACKING Jul: 2
COST | COP (USD/Kg FD) | 2.32 | 19 | Reduce city water usage | Use soft water for processing | Quyet Nguyen | OPs | Vu Le |  | Yes | No | Yes | Done |  | Jun Aug | Late | Vu Tran | Hai Le |  | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: NA; MONTHLY TRACKING Apr: NA; MONTHLY TRACKING May: NA; MONTHLY TRACKING Jun: 2; MONTHLY TRACKING Jul: 2 | 0 | 0 |  |  | 4080 m3 |  |  |  | 4128 m3 |  |  |  | 4128 m3 |  |  |  | 12336 m3
COMPLIANCE | No. of major finding from authorities |  | 54 | Environmental Protection | Zero coffee spent ground drop and release to environment (solid and wastewater) - Thay băng tải 701 - Done - Modify chương trình interlock băng tải khi vít tải 702 nghẹt - Done - Đấu lại chương trình cho motto SC702 (Không chạy qua biến tần) - Done - Set tần suất vệ sinh cho khu vực băng tải - Ongoing --> đã có PR/PO --> tiếp tục follow up --> đã có chương trình chờ kết nối --> W21 done | Nam Tran | Eng |  |  | No | Yes | No | NA |  | Apr May Jun Jul | late |  |  | 4 | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: NA; MONTHLY TRACKING Apr: 1; MONTHLY TRACKING May: 1; MONTHLY TRACKING Jun: 2; MONTHLY TRACKING Jul: 2
COST | COP (USD/Kg FD) | 2.32 | 29 | Reduce cost 5% Overhaul | Utilize local manpower instead of hiring experts ( software and hardware ) Improve innovation performance for equipment | Nam Truong | Eng | Thai Nguyen |  | Yes | No | No | NA |  | Jun | Done |  |  |  | NA | NA | NA | NA | NA | 4 | NA | NA | NA | NA | NA | NA
PEOPLE | Turnover of direct labor | 10% | 30 | Enhance career development & growth program | 50% SF to achieve Multi skill plan Build Shopfloor training program (onboarding program, competency matrix, career path,… Build Internal soft skill training plan (6 topics x 2 sessions/year ) | Thu Duong | HR |  |  | No | No | Yes | Done |  | Oct | On Progress | Yen Tran | Yen Tran | bar: MONTHLY TRACKING Jan to MONTHLY TRACKING Jul
COST | COP (USD/Kg FD) | 2.32 | 37 | Reduce Electric usage | Fine tuning Grasso parameter --> Trình bày trong meeting tháng 6 | Nam Tran | Eng |  |  | Yes | No | No | NA |  | Mar Apr May Jun Jul Aug | late | Nam Tran | Thang Cao | 5 | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: 2; MONTHLY TRACKING Apr: 2; MONTHLY TRACKING May: 2; MONTHLY TRACKING Jun: 2; MONTHLY TRACKING Jul: 2
COST | COP (USD/Kg FD) | 2.32 | 32 | Reduce steam usage | Install electrical pump to replace current pump - Done Makeup water for boiler on condensate tank (befor dosing at deairator tank) - Done | Nam Tran | Eng | Quang Vu |  | Yes | Yes | No | NA | Installed | Mar | Done | Thang Cao | Thang Cao |  | NA | NA | NA | 4 | NA | NA | NA | NA | NA | NA | NA | NA
COST | COP (USD/Kg FD) | 2.32 | 33 | Reduce steam usage | Separate LP & HP condensate water of boiler Control all steam traps to avoid steam leakage --> Monitoring | Nam Tran | Eng |  |  | Yes | Yes | No | NA |  | Mar | Done | Thang Cao | Thang Cao |  | NA | NA | NA | 4 | NA | NA | NA | NA | NA | NA | NA | NA
SAFETY | Loss time incident | 0 | 34 | Evacuation speaker system | Set up evacuation speaker system | Duc Nguyen | E2E |  |  | No | Yes | Yes | Done | TBC By BODs | Oct | On Progress | Hoang Nguyen | Thi Nguyen | bar: MONTHLY TRACKING Jan to MONTHLY TRACKING Jul
SAFETY | Loss time incident | 0 | 35 | BBS (Base behavior safety) | Run BBS program | Hoang Nguyen | SHE |  |  | No | No | No | NA | Ontime | Dec | On Progress | bar: MONTHLY TRACKING Jan to MONTHLY TRACKING Jul
SAFETY | Loss time incident | 0 | 36 | 5S stage 2 | 5S compliance (define stages following time) | Minh Thai | QA |  |  | No | No | No | NA | 3S (70% completion) | Sep | On Progress | Hoang Nguyen | Thi Nguyen | bar: MONTHLY TRACKING Jan to MONTHLY TRACKING Jul
OUTPUT | RW Generation (tons) | 50 | 8 | Reduce RW generation Late | Install a new aroma tank 1m3 to ensure a smooth changeover without aroma contamination --> waiting approval from BODs --> Oct | Duc Nguyen | Eng | Anh Truong | Process ENG | Yes | Yes | No | NA |  | Apr May Jun Jul Sep | late | Thang Cao | Thi Nguyen | 6 | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: NA; MONTHLY TRACKING Apr: 2; MONTHLY TRACKING May: 1; MONTHLY TRACKING Jun: 2; MONTHLY TRACKING Jul: 2
FOUNDATION | Department project/target |  | 53 | HRM System | Digital Time Attendance system and integrate with SAP B1 (IRS) system | Hong Vong | IT | Yen Tran Thu Duong | Huy Duong Hung Le Anh Truong Que Nguyen Duong Pham | Yes | Yes | Yes | Done |  | Jun Sep | Late | Yen Tran | Thi Nguyen | bar: MONTHLY TRACKING Jan to MONTHLY TRACKING Jul
COST | COP (USD/Kg FD) | 0 | 39 | Reduce steam usage | Zero steam water was leaked to drained sewage (storm water) --> Done Monitoring in Apr | Nam Tran | Eng |  |  | Yes | Yes | No | NA |  | Mar | Done | Hoang Nguyen | Thang Cao |  | NA | NA | NA | 4 | NA | NA | NA | NA | NA | NA | NA | NA
PEOPLE | Turnover of direct labor | 10% | 40 | WE mindset development On progress | Monthly Core value recognition program, re-visit monthly output competition - Done Build more employee feedback channels: HR QR, constructive feedback QR – Employees’ concern (10%) – Response ontime rate (100%) – Review action plan Quarterly Recognition - Done Annual engagement plan Bi- yearly Employees Engagement survey (80%) | Dao Nguyen | HR |  |  | No | No | No | NA |  | Mar Apr May Jun Jul | late | Yen Tran | Thi Nguyen |  | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: NA; MONTHLY TRACKING Apr: 2; MONTHLY TRACKING May: 2; MONTHLY TRACKING Jun: 2; MONTHLY TRACKING Jul: 2
PEOPLE | Turnover of direct labor | 10% | 41 | Performance management On progress | Refresh Performance management training - On going 100% individual objective setting on time (Objective cascading in 10-Feb) - Done 100% Regular appraisal: Quarter checking, mid-year review, end of year - On going Link % Merit & Bonus payout - Done | Thu Duong | HR |  |  | No | No | No | NA |  | Mar Apr May Jun Jul | late | Yen Tran | Thi Nguyen |  | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: NA; MONTHLY TRACKING Apr: 2; MONTHLY TRACKING May: 2; MONTHLY TRACKING Jun: 2; MONTHLY TRACKING Jul: 2
COMPLIANCE | No. of major finding from authorities | 0 | 42 | Environmental Protection | Install after burner system to reduce CO in roaster air emission below 800 mg/Nm3 | Duc Nguyen | E2E |  |  | No | Yes | Yes | Done | TBC By BODs | Dec | On Progress | Hoang Nguyen | Thi Nguyen | bar: MONTHLY TRACKING Jan to MONTHLY TRACKING Jul
COMPLIANCE | No. of major finding from authorities | 0 | 43 | Tax Reporting | VAS_CIT/ WHT 2026 no major finding | Trang Dao | FC |  |  | No | No | No | NA |  | Dec | On Progress | bar: MONTHLY TRACKING Jan to MONTHLY TRACKING Jul
COMPLIANCE | Cert. renewal | 100% | 44 | Reduce hard-copy record and ECRS documented standard | Reduce 40% hard-copy record, convert into digital data/record. ECRS Documentated Standard | Binh Dang | QA | Hồng Vọng | Quế Nguyễn | No | Yes | Yes | Done | Simplify 30% documentation and convert into digital 40% record | Sep | On Progress | Dung Tran | Thi Nguyen | bar: MONTHLY TRACKING Jan to MONTHLY TRACKING Jul
FOUNDATION | Department project/target |  | 45 | Sales & Planning | Sales Volume - 5550mt Production volume ratio management – 49.6/50.4 Supply & Demand Planning on time – 100% FGs Inventory management - 300mt | Thong Nguyen | SC | Duong Pham |  | No | No | No | NA |  | Dec | On Progress | bar: MONTHLY TRACKING Jan to MONTHLY TRACKING Jul
FOUNDATION | Department project/target |  | 46 | Procurement | PR-PO management – 93% On time delivery – 90% | Tuyen Do | SC | Quynh Nguyen |  | No | No | No | NA |  | Dec | On Progress | bar: MONTHLY TRACKING Jan to MONTHLY TRACKING Jul
FOUNDATION | Department project/target |  | 47 | Import - Export | Accuracy in documentation – 100% No delay in Delivery & Receiving – 98% Less cost arise : 1% | Khanh Nguyen | SC | Thong Nguyen |  | No | No | No | NA |  | Dec | On Progress | bar: MONTHLY TRACKING Jan to MONTHLY TRACKING Jul
FOUNDATION | Department project/target |  | 48 | Warehouse | Loading capacity: 3 conts/day Tipping capacity: 55mt/day GB Warehouse capacity: 1500mt Accuracy in Tipping loss tracking: 100% | Truong Tran | SC |  |  | No | No | No | NA |  | Dec | On Progress | bar: MONTHLY TRACKING Jan to MONTHLY TRACKING Jul
FOUNDATION | Department project/target |  | 49 | SAP system & Improvement | SO – Invoice – Packing list template improvement SSCC pick up automation in SO BOM breakdown report Master data of HS code Outsource labor timesheet checking template for payment -> Done | Duong Pham | SC | Khanh Nguyen Thong Nguyen |  | No | No | No | NA |  | Apr May Jun Jul | late | Hang Tran | Hang Tran |  | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: NA; MONTHLY TRACKING Apr: 2; MONTHLY TRACKING May: 2; MONTHLY TRACKING Jun: 2; MONTHLY TRACKING Jul: 2
FOUNDATION | Department project/target |  | 50 | SAP system | Accounting: AR + AP standardize mapping/ reporting | Trang Dao | FC |  |  | No | No | No | NA |  | Dec | On Progress | bar: MONTHLY TRACKING Jan to MONTHLY TRACKING Jul
FOUNDATION | Department project/target |  | 51 | One stream System (LDC) | Standardize report mapping LDC report - Done | Hang Ho | FC |  |  | No | No | No | NA |  | Mar | Done | Diem Nguyen | Diem Nguyen |  | NA | NA | NA | 4 | NA | NA | NA | NA | NA | NA | NA | NA
FOUNDATION | Department project/target |  | 52 | SAP system | Auto Cost report to off-takers | Hang Ho | FC |  |  | No | No | No | NA |  | Dec | On Progress | bar: MONTHLY TRACKING Jan to MONTHLY TRACKING Jul
OUTPUT | Volume (tons FD) | 5550 | 3 | Reduce EPL < 2.5% | Revisit & Reduce EPL 2025 Implement Improvement list 2026 Support key performance of CI team Re-apply Work order & routine tracking | Anh Truong | Eng | Nam Truong Thai Nguyen |  | Yes | Yes | Yes | Done | < 2.5% | May Jun Jul | Done | Duy Nguyen | Thi Nguyen |  | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: NA; MONTHLY TRACKING Apr: NA; MONTHLY TRACKING May: 1; MONTHLY TRACKING Jun: 2; MONTHLY TRACKING Jul: 4
COST | Yield of VG2 Yield of Conilon | 2.01 2.00 | 24 | Reduce manufacturing loss from 5% to 4.5% | Install filter before clarifier --> Installed --> nghẹt filter, cần review lại --> change to the filter 500 micro. Est ~ đầu tháng 6 --> re-test ok Connect sludge discharge from clarifiers to thin tank --> propose phương án Utilize current decanter from SGS area --> trial progress | Duc Nguyen | Eng |  | ENG | Yes | Yes | No | NA |  | Mar Apr May Jun Jul Aug | late | Thang Cao | Thi Nguyen | 6 | MONTHLY TRACKING Jan: NA; MONTHLY TRACKING Feb: NA; MONTHLY TRACKING Mar: NA; MONTHLY TRACKING Apr: 2; MONTHLY TRACKING May: 1; MONTHLY TRACKING Jun: 2; MONTHLY TRACKING Jul: 2
Note on F6: Hai Le:
Note on Q16: Nam Tran: Done 15/6/2026, duy trì tracking đánh giá tiêu thụ city water/MTFD trước và sau modify
Note on Q21: Nam Tran: Done 15/6/2026, duy trì tracking đánh giá tiêu thụ city water/MTFD trước và sau modify
Note on Q26: Nam Tran: Đã gửi anh HOÀNG CSD cho boiler/bimomass

## MoM
Minutes of Meeting
No | Review Date | Project | Activities | Leader | Comment | Timing | Status | Finish time
1 | 2026-03-20 | Reduce city water usage | Change makeup water for Boiler from RO to soft water - Done | Nam Tran | Completed | Jan | Done | Shutdown in Jan
2 | 2026-03-20 | Sustain speed of FD at 750 kg/h | Increase TS = 49% Standardize FD parameters after increase TS to 49% | Duy Le | Completed Project Some comments from a Thi: 1. Đảo bảo duy trì Speed để đạt được target Volume, tuy nhiên cần chú trọng đảm bảo chất lượng đi đôi với sản lượng 2. Listdown các parameters đã thay đổi (Before/After) 3. Kết hợp với Maintenance team to imrprove UPs (OPL/EPL) tại FD | Mar | Done | 2026-01-01
3 | 2026-03-20 | Increase capacity of Devex line to 780 kgs/h | Increase cell load Reduce cycle time Increase Evap running time from 32 hrs to 48 hrs | Quang Vu | MTD: 760 kg/hr - On progress Comments: 1. Check lại điều kiện chạy Moisturing sau khi Acceptance test with Devex (đạt/ 0 đạt ???) 2. Set ưu tiên cho các action đã define nhằm focus vào các action chính 3. Collect data nghẹt (đường ống/valve/HX…) để xác định thời rõ thời gian vệ sinh/thay thế/sửa chữa/Prepare spare part/.... | Mar | Late
4 | 2026-03-20 | Reduce Monthly Planned Stop at Extraction from 46 hours to 38 hours | Reduce EXT CIP from 16 hours to 14 hours Reduce Pressure Test & Start up from 12hrs to 8 hours | Quang Vu | MTD: 42,5 hrs - On progress Comments: 1. Production/Engineering cùng discuss để đưa ra/review & aligned các action hỗ trợ cho việc giảm PS tại Ext (Review trong weekly meeting) 2. Study lắp thêm 1 hệ thống CIP (đánh giá kĩ việc lắp thêm có giúp giảm thời gian CIP or tăng hiệu quả CIP hay không? Nếu có --> propose solution ) 3. All team tập trung support EXT để đảm bảo cung cấp đủ dịch cho line FD & volume hàng liquid | Mar | Late
5 | 2026-03-20 | Reduce Monthly Planned Stop at Extraction from 46 hours to 38 hours | Reduce CIP time by installing a new tank to collect wastewater from Extraction CIP (Utility) | Nam Tran |  | Mar | Late
6 | 2026-03-20 | Q-line mapping for Micro ( Reduce 50% NCP due to Micro) | With Production: Normal production: 100% production normal operation mapped CIP/COP: 100% cleaning operation mapped | Binh Dang | On progress Comments: 1. Data collection for NC of micro (target/tháng, MTD,…) 2. Review & đánh giá kĩ các actions đã triển khai (giảm cycle hồi sediment, ép bã,…) 3. Standardize các điều kiện/thông số chuẩn (critical imapct) để duy trì kiểm soát vi sinh tại từng cụm thiết bị --> Move due date to Jun | Jun | Done | Monitoring to Dec
7 | 2026-03-20 | Q-line mapping for FB (Reduce 90% wet RW volume due to FB) | With Production: Normal production: 100% production normal operation mapped CIP/COP: 100% cleaning operation mapped With Maintenance: 100% Maintenance operation mapped | Binh Dang | On progress Comments: 1. Focus đưa ra action để giải quyết complaint liên quan đến FB carton tại FP 2. Nên có danh sách quản lý thiết/tools tại các khu vực sản phẩm hở đã được approval sử dụng 3. Các hoạt động có mối nguy FB cần thực hiện Wrok permit để kiểm soát 4. Nên tạo checklist kiểm soát công cụ dụng cụ sau khi vệ sinh/bảo trì --> Move due date to Jun | Jun | Done | Monitoring to Dec
8 | 2026-03-20 | Sustain yield 60.5% | Re-visit & reduce OPL 2025 of Extraction | Quang Vu | MTD: 60,5 - 61% Action - On progress Follow up action đã define trong weekly meeting, các actions cần được discuss & aligned trước khi thực hiện nhầm mitigates rủi ro (nếu có) | Mar | Late
9 | 2026-03-20 | Sustain yield 60.5% | Re-visit & reduce EPL 2025 of Extraction | Nam Truong |  | Mar | Late
10 | 2026-03-20 | Sustain yield 60.5% | Re-visit & reduce UPs 2025 of Utility | Nam Tran |  | Mar | Late
11 | 2026-03-20 | Burn protection | 100% flanges are covered at 2nd floor | Nam Truong | Installed Completed on 2nd floor | Mar | Done | Jun
12 | 2026-03-20 | Reduce manufacturing loss from 5% to 4.5% | Finetuning the parameters of Clarifiers & Evaporation | Trieu Phan | Completed Project Monthly review to track the results and ensure sustainability | Mar | Done | 2026-01-01
13 | 2026-03-20 | Reduce manufacturing loss from 5% to 4.5% | Install filter before clarifier Connect sludge discharge from clarifiers to thin tank Utilize current decanter from SGS area | Duc Nguyen | On progress Follow up in Internal meeting from ENG & update the result to team | Mar | Late
14 | 2026-03-20 | Fire protection | Zero error fire alarm issue | Nam Tran | On progress | Mar | Late
15 | 2026-03-20 | CSD (Critical Safety Device) | Apply CSD for dust at boiler | Nam Tran | On progress Follow up in Internal meeting from ENG & update the result to team | Mar | Done
16 | 2026-03-20 | Reduce steam usage | Install electrical pump to replace current pump | Nam Tran | Installed Follow up in Internal meeting from ENG & update the result to team | Mar | Done | 2026-03-28
17 | 2026-03-20 | Reduce steam usage | Separate LP & HP condensate water of boiler Control all steam traps to avoid steam leakage | Nam Tran | Completed Follow up in Internal meeting from ENG & update the result to team | Mar | Done | 2026-03-28
18 | 2026-03-20 | Reduce Electric usage | Fine tuning Grasso parameter | Hung Le | On progress Follow up in Internal meeting from ENG & update the result to team | Mar | Late
19 | 2026-03-20 | Reduce WWT cost | Burn sludge from WWT Plant in Boiler Study to Sale sludge to Fertilizer | Nam Tran | On progress Follow up in Internal meeting from ENG & update the result to team | Mar | Late
20 | 2026-03-20 | Environmental Protection | Zero coffee spent ground drop and release to environment (solid and wastewater) Zero steam water was leaked to drained sewage (storm water) | Nam Tran | On progress Follow up in Internal meeting from ENG & update the result to team | Mar | Late
21 | 2026-03-20 | WE mindset development | Monthly Core value recognition program, re-visit monthly output competition Build more employee feedback channels: HR QR, constructive feedback QR – Employees’ concern (10%) – Response ontime rate (100%) – Review action plan Quarterly Recognition Annual engagement plan Bi- yearly Employees Engagement survey (80%) | Dao Nguyen | On progress Follow up in Internal meeting from HR & update the result to team | Mar | Late
22 | 2026-03-20 | Performance management | Refresh Performance management training 100% individual objective setting on time (Objective cascading in 10-Feb) 100% Regular appraisal: Quarter checking, mid-year review, end of year Link % Merit & Bonus payout | Thu Duong | On progress Follow up in Internal meeting from HR & update the result to team | Mar | Late
23 | 2026-03-20 | One stream System (LDC) | Standardize report mapping LDC report | Hang Ho | Completed Follow up in Internal meeting from FC & update the result to team | Mar | Done | March
24 | 2026-03-20 | Reduce steam usage | Zero steam water was leaked to drained sewage (storm water) --> Done Monitoring in Apr | Nam Tran | Completed Monitor result effectiveness | Mar | Done | March
25 | 2026-04-22 | Reduce Monthly Planned Stop at Extraction from 46 hours to 38 hours | Reduce Maintenance time from 18 hrs to 16hrs | Nam Truong | MTD: 17 hrs Complete the remaining action to achieved target in May | Apr | Late
26 | 2026-04-22 | Reduce RW generation | Reduce/Eliminate the defect 2025 Finetuning the standard & SOP Final CHO matrix | Vu Le | MTD: 1420kg Most of action defined are completed Combine the remaining action related to FB in the Project of Binh Dang Continue monitor result effectiveness | Apr | Done | April
27 | 2026-04-22 | Reduce RW generation | Install a new aroma tank 1m3 to ensure a smooth changeover without aroma contamination | Duc Nguyen | Discuss with a Duy Nguyen to get support | Apr | Late
28 | 2026-04-22 | Reduce Electric usage | Install solar system (6.6% generate contribution) | Duc Nguyen | Installed Calculate the saving in Quarter 2 | Apr | Done | April
29 | 2026-04-22 | SAP system & Improvement | SO – Invoice – Packing list template improvement SSCC pick up automation in SO BOM breakdown report Master data of HS code Outsource labor timesheet checking template for payment - Done | Duong Pham | Continue follow up the action defined Send the evidence after completed project | Apr | Late
30 | 2026-04-22 | Environmental Protection | Zero coffee spent ground drop and release to environment (solid and wastewater) | Nam Tran | PR/PO created Continue follow up with SC to complete actions. | Apr | Late
31 | 2026-05-15 | Reduce EPL < 2.5% | Revisit & Reduce EPL 2025 Implement Improvement list 2026 Support key performance of CI team Re-apply Work order & routine tracking | Anh Truong | Comment: 1. Collect lại chính xác total EPL (YTD) 2. Thêm data các sự cố tại Utility --> action to reduce 3. Xây dựng quy trình chuẩn & triển khai cho nhà thầu khi hỗ trợ shutdown, đảm bảo kiểm tra trước khi bàn giao cho nhà máy 4. Nên xây dựng hệ thống kiểm tra toàn diện sau khi bảo trì (SOP/WI), đảm bảo hệ thống restart smoothly. 5. Apply trực quan hóa các điểm kiểm soát thiết bị, high focus to FD | May
32 | 2026-05-15 | Increase capacity of Devex line to 780 kgs/h | Increase cell load Reduce cycle time Increase Evap running time from 32 hrs to 48 hrs | Quang Vu | EXT Capacity in May: 815kg/h Comment: List down các yếu tố ảnh hưởng đến capacity (ACN, downstream,..) & % mức độ impact --> Trial tăng running time of clarifier to 10h, 12h (đánh giá step by step) --> Đánh giá lượng cặn hồi về từ sediment tank (impact ntn đến hoạt động clarifier
33 | 2026-05-15 | Reduce Monthly Planned Stop at Extraction from 46 hours to 38 hours | Reduce EXT CIP from 16 hours to 14 hours Reduce Pressure Test & Start up from 12hrs to 8 hours | Quang Vu | YTD: 42,5 hrs Comment: 1. Tính toán lượng caustic nếu xả về WWTP (1 tháng/lần) 2. Study nếu gắn thêm bộ lọc cặn xút để giảm thời gian vệ sinh --> Eng support thiết kế bộ lọc thuận tiện cho việc tháo lắp
34 | 2026-05-15 | Sustain yield 60.5% | Re-visit & reduce OPL 2025 of Extraction | Quang Vu | Comment: Study phương án chạy Ext tối ưu nhất để đạt được target GY 1.99
35 | 2026-05-15 | Sustain yield 60.5% | Re-visit & reduce EPL 2025 of Extraction | Nam Truong | Comment: Cần collect thông tin EPL của Ext để lên kế hoạch cụ thể Report present in Jun
36 | 2026-05-15 | Reduce Monthly Planned Stop at Extraction from 46 hours to 38 hours | Reduce Maintenance time from 18 hrs to 16hrs | Nam Truong | PS in May: 15 hrs Comment: Kết hợp Prod để lên kế hoạch dừng line tối ưu nhất Chuẩn hóa maintenance task khi shutdown, report present in Jun
37 | 2026-05-15 | Reduce Monthly Planned Stop at Extraction from 46 hours to 38 hours | Reduce CIP time by installing a new tank to collect wastewater from Extraction CIP (Utility) | Nam Tran | Comment: Complete end of May
38 | 2026-05-15 | Fire protection | Zero error fire alarm issue | Nam Tran | Comment: Discuss with a Hoang to implementation
39 | 2026-05-15 | CSD (Critical Safety Device) | Apply CSD for dust at boiler | Nam Tran | Comment: Discuss with a Hoang to implementation Completed and sent to Hoang Nguyen | Mar | Done | Jun
40 | 2026-05-15 | Environmental Protection | Zero coffee spent ground drop and release to environment (solid and wastewater) Zero steam water was leaked to drained sewage (storm water) | Nam Tran | Comment: Đã tạo chương trình cho băng tải, chờ kết nối vào W21
41 | 2026-05-15 | Reduce Electric usage | Fine tuning Grasso parameter | Hung Le | Comment: Tạo report present in Jun
42 | 2026-05-15 | Reduce RW generation | Install a new aroma tank 1m3 to ensure a smooth changeover without aroma contamination | Duc Nguyen | Comment: Waiting approval from BOD
43 | 2026-05-15 | Reduce manufacturing loss from 5% to 4.5% | Install filter before clarifier Connect sludge discharge from clarifiers to thin tank Utilize current decanter from SGS area | Duc Nguyen | Comment: Should be separate to each activity Book meeting discuss to implementation
44 | 2026-06-19 | Digital Time Attendance system and integrate with SAP B1 (IRS) system | Time attendence system: golive on 18-Jun - Done Intergrate SAP B1 - Estimate complete on Sep | Hong Vong | Move due date to Sep Input timeline for each action in presentation | Jun | Late | Est Sep
45 | 2026-06-19 | Q-line mapping for Micro (Reduce 50% NCP due to Micro) | YTD: Reduce 61% based on NC in 2025 | Bình Đặng | Continue follow up action plan for monitoring | Jun | Done | Jun
46 | 2026-06-19 | Q-line mapping for FB (Reduce 90% wet RW volume due to FB) | YTD: 4950kg RW FB due to FB Reduce 87% based on RW FB 2025 | Bình Đặng | Strengthen & monitoring action plan to Dec | Jun | On going | Monitoring to Dec
47 | 2026-06-19 | Reduce OPL <2.5% | YTD: 3.14% | Vu Le | Follow up action plan to reach the target | Jun | Late
48 | 2026-06-19 | Sustain yield 60.5% | Re-visit & reduce UPs 2025 of Utility | Nam Trần | Collect data to create presentation | Jun | Late
49 | 2026-06-19 | Reduce city water usage | Saving RO reject to RAW water tank | Nam Trần | List down activities completed Collect data to verify saving achievement | Jun | Late
50 | 2026-06-19 | Reduce city water usage | Re-use condensate water and bad Aroma to WWTP - Ongoing | Nam Trần | Following action | Jun | Late
51 | 2026-06-19 | Reduce Maintenance Opex in Utility | Optimize spare part of WTP Find local supplier to reduce spare part price (similar quality) | Nam Trần | Following action | Jun | Late
52 | 2026-06-19 | Reduce WWT cost | Burn sludge from WWT Plant in Boiler Study to Sale sludge to Fertilizer | Nam Trần | Following action | Jun | Late
53 | 2026-06-19 | Reduce city water usage | Re-use condensate water from process | Quyet Nguyen | Project completed Work with Utility to calculate the savings | Jun | Done | 2026-04-21
54 | 2026-06-19 | Reduce city water usage | Use soft water for processing | Quyet Nguyen |  | Jun | Late
55 | 2026-06-19 | Reduce cost 5% Overhaul | Utilize local manpower instead of hiring experts ( software and hardware ) Improve innovation performance for equipment | Nam Truong | Project completed Work with FC to calculate the savings | Jun | Done | March
1 | 2026-07-17 | Reduce Monthly Planned Stop at Extraction from 46 hours to 38 hours | Reduce Maintenance time from 18 hrs to 16hrs Actual aintenance time in Jul: 16 hrs | Nam Truong | Bị ảnh hưởng gần 3 hrs do thời gian chết khi chờ nhà thầu --> monitor thêm và chuẩn hóa maintenance activities | Apr May Jun Jul Sep | late
2 | 2026-07-17 | Sustain yield 60.5% | Re-visit & reduce EPL 2025 of Extraction | Nam Truong | Work with production to close the remaining Ext issue | Mar Apr May Jun Jul Sep | late
3 | 2026-07-17 | Sustain yield 60.5% | Re-visit & reduce UPs 2025 of Utility | Nam Tran | Collect data to create presentation | Jun Jul | Late
4 | 2026-07-17 | Reduce Monthly Planned Stop at Extraction from 46 hours to 38 hours | Reduce CIP time by installing a new tank to collect wastewater from Extraction CIP (Utility) Actual: Survey, SOW, PR =>Done, ongoing next steps | Nam Tran | Installed | Mar Apr May Jun Jul | Done | Jul
5 | 2026-07-17 | Fire protection | Zero error fire alarm issue --> Đã lên PR --> Review -> Lên PO trong tháng 5 | Nam Tran | Pending | Mar Apr May Jun Aug | late
6 | 2026-07-17 | Reduce city water usage | Saving RO reject to RAW water tank | Nam Tran | Completed Monitor city water saving in Quarter 3 | Jun | Done | 2026-06-13
7 | 2026-07-17 | Reduce Maintenance Opex in Utility | Optimize spare part of WTP Find local supplier to reduce spare part price (similar quality) | Nam Tran | Pending | Jun Jul | Late
8 | 2026-07-17 | Reduce city water usage | Reuse condensate from process for WWTP - On going | Nam Tran | Pending | Jul | Late
9 | 2026-07-17 | Environmental Protection | Zero coffee spent ground drop and release to environment (solid and wastewater) - Thay băng tải 701 - Done - Modify chương trình interlock băng tải khi vít tải 702 nghẹt - Done - Đấu lại chương trình cho motto SC702 (Không chạy qua biến tần) - Done - Set tần suất vệ sinh cho khu vực băng tải - Ongoing --> đã có PR/PO --> tiếp tục follow up --> đã có chương trình chờ kết nối --> W21 done | Nam Tran | Pending | Apr May Jun Jul | late
10 | 2026-07-17 | Reduce cost 5% spare part for Extraction and Transport system | Savings cost of spare part fabrication workshop Contribute to reduce the store spare part over 36 months costs 10% Refurbishing part to reduce purchasing | Nam Truong | Work with FC to get data the budget of spare part in 2025 | Jul | Late
11 | 2026-07-17 | Reduce Electric usage | Fine tuning Grasso parameter --> Trình bày trong meeting tháng 6 | Hung Le | Pending | Mar Apr May Jun Jul Aug | late
12 | 2026-07-17 | Reduce RW generation Late | Install a new aroma tank 1m3 to ensure a smooth changeover without aroma contamination --> waiting approval from BODs | Duc Nguyen | In details design phase | Apr May Jun Jul Sep | late
13 | 2026-07-17 | Reduce EPL < 2.5% | Revisit & Reduce EPL 2025 Implement Improvement list 2026 Support key performance of CI team Re-apply Work order & routine tracking | Anh Truong | YTD: ~1.2% Final presentation & showcase | May Jun Jul | Done
14 | 2026-07-17 | Reduce manufacturing loss from 5% to 4.5% | Install filter before clarifier --> Installed --> nghẹt filter, cần review lại --> change to the filter 500 micro. Est ~ đầu tháng 6 Connect sludge discharge from clarifiers to thin tank --> propose phương án Utilize current decanter from SGS area --> trial progress | Duc Nguyen | Brainstorm next action | Mar Apr May Jun Jul Aug | late
1 | 2026-08-21 | Reduce OPL <2.5% | Revisit & Reduce OPL 2025 Create/update the operations std --> Action pending Average: Jan to May: 3.14% | Vu Le | YTD: 2.45% | Aug
2 | 2026-08-21 | Increase capacity of Devex line to 780 kgs/h --> Actual: 760 kg/hr | Increase cell load from 395 -> 400 Actual: 400 (Done) Reduce cycle time from 19 -> 17 Actual: 18 mins (On going) -Done Increase Evap running time from 32 hrs to 48 hrs Actual: 40 hrs (Done) | Quang Vu | YTD: 790 Cần liệt kê top 3 issues và % impact đến Capacity EXT từ đó đưa ra action để improve Xem lại các yếu tố thực sự ảnh hưởng đến Ext Capacity và & impacted | Sep
3 | 2026-08-21 | Reduce Monthly Planned Stop at Extraction from 46 hours to 38 hours MTD: 42,5 hrs | Reduce EXT CIP from 16 hours to 14 hours. Actual: 16 (On going) - CIP program 10 cell thay cho CIP 5 cell/1 lần - Done - Trial CIP không tháo Bottom Filter -Done - Các task tháo mở top filter, thiết bị để CIP -> Phối hợp bảo trì để làm nhanh nhất có thể. Reduce Pressure Test & Start up from 12hrs to 8 hours. Actual 11 hrs (On going) - Trial Pressure test bằng Steam, thay bằng nước- đã trial 1 lần vào tháng 2 -Done - Tăng cường nhân lực kiểm tra trong quá trình thay ống và valve để giảm mistake. | Quang Vu | YTD: ~47 hrs Cần liệt kê top 3 issues và % impact đến PS o EXT từ đó đưa ra action để improve Các phương án đề xuất cải tiến cần được align với các bộ phận liên quan trước khi propose lên. | Sep
4 | 2026-08-21 | Sustain yield 60.5% Sustain: 60.5% | Re-visit & reduce OPL 2025 of Extraction Top 3 issues: 1. Bottom filter blockage - Plan thay ống định kỳ hàng tháng - opimize lại plan thay ống hiệu quả. Phối hợp với MT cùng nhau work trong ngày shutdown 2. SE & PE filter are blockage - SE: Gắn thêm đường ống song song - có thể chạy by pass - PE: Gắn thêm 1 Rotary Fillter -> swith chạy qua lại -> Giảm downtime. (Pending ) - PE: Gắn đường ống say Rotary valve lớn hơn, Gắn đường nước rửa cho lọc + đường ống PE sau lọc -Done 3. Piping blockage of the end of cycle - Plan thay ống định kỳ hàng tháng - opimize lại plan thay ống hiệu quả. Phối hợp với MT cùng nhau work trong ngày shutdown | Quang Vu | YTD: 790 Cần liệt kê top 3 issues và % impact đến Ext Yield từ đó đưa ra action để improve Tính toán % Ext Yield = Est Dry Yield để đánh giá sự ảnh hưởng. Xem lại các yếu tố thực sự ảnh hưởng đến Ext Yield | Sep
5 | 2026-08-21 | Reduce Monthly Planned Stop at Extraction from 46 hours to 38 hours MTD: 17 hrs | Reduce Maintenance time from 18 hrs to 16hrs | Nam Truong | YTD: 15 hrs Cần phối hợp với Prod và Planner để adjust plan phù hợp, tránh thời gian dừng chờ lãng phí Ngoài thời gian cần đạt được, cũng cần focus vào chất lượng bảo trì để tránh bị issue khi restart. | Sep
6 | 2026-08-21 | Sustain yield 60.5% | Re-visit & reduce EPL 2025 of Extraction | Nam Truong | Reduce unplanned stops by ~50% compared to 2025 Listdown before/after và % contribution của từng action để đánh giá mức độ hiệu quả | Sep
7 | 2026-08-21 | Reduce cost 5% spare part for Extraction and Transport system | Savings cost of spare part fabrication workshop Contribute to reduce the store spare part over 36 months costs 10% Refurbishing part to reduce purchasing | Nam Truong | Reduce Spare part cost of Ext and transport system ~20% Reduce spare part inventory ~ 5% | Aug

## Summary
Total Project | Project charter | Sponsored by HODs | Signed | Sponsored by a Thi | Signed |  | ILD PROJECT TRACKING
54 | 28 | 11 | 2/11 | 17 | 0/17
Leader | Department | Summary | Sponsor by |  |  |  | Month | Total Project | Status
|  |  | HODs | GD | Signed | Completed |  |  | Completed | Late | On going
|  | 28 | 11 | 17 | 5 | 8 | Jan | 1 | 1 | 0 | 0
Duc Nguyen | ENG | 3 | 0 | 3 | 0 | 1 | Feb | 0 | 0 | 0 | 0
Thu Duong | HR | 1 | 0 | 1 | 0 |  | Mar | 18 | 10 | 8 | 0
Hong Vong | IT | 1 | 0 | 1 | 0 |  | Apr | 6 | 1 | 5 | 0
Anh Truong | ENG | 1 | 0 | 1 | 0 |  | May | 1 | 1 | 0 | 0
Nam Truong | ENG | 2 | 0 | 2 | 0 |  | Jun | 12 | 5 | 7 | 0
Duy Le | OPs | 2 | 1 | 1 | 0 | 1 | Jul | 2 | 0 | 2 | 0
Vu Le | OPs | 2 | 2 | 0 | 2 | 1 | Aug | 0 |  |  | 0
Quang Vu | OPs | 3 | 3 | 0 | 0 |  | Sep | 3 |  |  | 3
Trieu Phan | OPs | 1 | 1 | 0 | 1 | 1 | Oct | 2 |  |  | 2
Quyet Nguyen | OPs | 2 | 1 | 1 | 0 | 1 | Nov | 0 |  |  | 0
Binh Dang | QA | 3 | 2 | 1 | 2 | 2 | Dec | 9 |  |  | 9
Nam Tran | ENG | 7 | 1 | 6 | 0 | 1 | Sum | 54 | 18 | 22 | 14
Key Drivers |  | No. of Project | Completed | On going | Completed Rate
Output |  | 9 | 4 | 5 | 44.44%
Cost |  | 21 | 9 | 12 | 42.86%
People |  | 3 | 0 | 3 | 0%
Compliance |  | 4 | 0 | 4 | 0%
Customer complaint |  | 2 | 2 | 0 | 100%
Safety |  | 6 | 2 | 4 | 33.33%
Foundation |  | 9 | 1 | 8 | 11.11%
|  | 54 | 18 | 36 | 33.33%
Note on D20: Duy Pham: 1.Increase FD Capaciy 2.Reduce RW generation 3.Reduce EPL 4.Installing a new tank to collect wastewater from Extraction CIP (Utility)
Note on D21: Duy Pham: 1.Reduce manufacturing loss 2.Change makeup water for Boiler from RO to soft water 3.Install solar system 4.Install electrical pump to replace current pump Makeup water for boiler on condensate tank (befor dosing at deairator tank) 5.Separate LP & HP condensate water of boiler 6.Zero steam water was leaked to drained sewage (storm water) 7. Re-use condensate water from process 8.Utilize local manpower instead of hiring experts 9.Saving RO reject to RAW water tank
Note on D24: Duy Pham: 1. Q line mapping - Micro 2. Q line mapping - FB
Note on D25: Duy Pham: 1. Apply CSD from Boiler 2. 100% flanges are covered at 2nd floor
Note on D26: Duy Pham: 1.Standardize report mapping LDC

## Sheet1
SUMMARY PROJECT 2026
Month | No of Project | Completed Ontime | % Completed Ontime | Completed | Late | Ongoing | QUARTERLY |  |  | HALF YEAR |  |  | FULL YEAR
[7 empty] | % Completed | % Late | % Ongoing | % Completed | % Late | % Ongoing | % Completed | % Late | % Ongoing
Jan | 1 | 1 | 36.84% | 1 | 0 | 0 | 57.89% | 42.11% | 0% | 47.37% | 52.63% | 0% | 33.33% | 40.74% | 25.93%
Feb | 0 | 0 |  | 0 | 0 | 0
Mar | 18 | 6 |  | 10 | 8 | 0
Apr | 6 | 2 | 36.84% | 1 | 5 | 0 | 36.84% | 63.16% | 0%
May | 1 | 0 |  | 1 | 0 | 0
Jun | 12 | 5 |  | 5 | 7 | 0
Jul | 2 | 0 | 0% | 0 | 2 | 0 | 0% | 40% | 60% | 0% | 12.5% | 87.5%
Aug | 0 |  |  |  | 0 | 0
Sep | 3 |  |  |  | 0 | 3
Oct | 2 |  | 0% |  | 0 | 2 | 0% | 0% | 100%
Nov | 0 |  |  |  | 0 | 0
Dec | 9 |  |  |  | 0 | 9
| 54 | 14 | 25.93% | 18 | 22 | 14